## project_data
Project ID | Project Name | Division | PIC | Progress | Due Date | Issue | Countermeasure | Risk | Status
P001 | Battery Localization | Production | Andi | 72 | 2026-06-15 | Supplier Delay | Escalation Meeting | High | Red
P002 | EV Dashboard System | IT | Budi | 88 | 2026-06-25 | Minor UI Delay | Additional Resource | Medium | Yellow
P003 | Smart Logistics | SCM | Rina | 95 | 2026-06-10 | None | Monitoring | Low | Green